## Development
GANTT CHART FOR BOOKED
= Idle/Target Defense Dates | January 15, 2018 | [5 empty] | January 22, 2018 | [5 empty] | January 29, 2018 | [5 empty] | February 5, 2018 | [5 empty] | February 12, 2018 | [5 empty] | February 19, 2018 | [5 empty] | February 26, 2018 | [5 empty] | March 05, 2018 | [5 empty] | March 12, 2018 | [5 empty] | March 19, 2018 | [5 empty] | March 26, 2018 | [5 empty] | April 02, 2018 | [5 empty] | April 09, 2018
Task Name | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S
1 Development for Prelims | bar: January 15, 2018 M to February 5, 2018 W
1.1 Set-up Project repository | bar: January 15, 2018 M to January 15, 2018 T
1.2 Log-in | bar: January 15, 2018 W to January 15, 2018 F
1.3 Registration page | bar: January 15, 2018 S to January 22, 2018 T
1.4 Home screen/Feed | bar: January 22, 2018 W to January 22, 2018 S
1.5 Search for books | bar: January 29, 2018 M to January 29, 2018 T
1.6 Upload book | bar: January 29, 2018 F to February 5, 2018 T
1.7 50% Working System | bar: February 5, 2018 W
2 Development for Midterms | bar: February 5, 2018 T to March 05, 2018 T
2.1 Account page/Settings | bar: February 5, 2018 T to February 12, 2018 M
2.2 Location Tracker | bar: February 12, 2018 T to February 19, 2018 M
2.3 Chat | bar: February 19, 2018 T to February 19, 2018 W
2.4View Owned books/rented Books | bar: February 19, 2018 T to February 19, 2018 S
2.5 Report page | bar: February 26, 2018 M to February 26, 2018 W
2.6 Request | bar: February 26, 2018 T to February 26, 2018 S
2.7 Debugging and Revisions | bar: March 05, 2018 M
2.8 100% Working system | bar: March 05, 2018 T
2.9 Usability Testing | bar: March 05, 2018 W to March 05, 2018 T
3 Development for Finals | bar: March 05, 2018 F to April 09, 2018 S
3.1 Checking of the system | bar: March 26, 2018 W to April 02, 2018 S
3.2 CD of the application | bar: April 09, 2018 M to April 09, 2018 T
3.3 Video Pitching | bar: April 09, 2018 W to April 09, 2018 S

## Documents
GANTT CHART FOR BOOKED
= Idle/Target Defense Dates | January 15, 2018 | [5 empty] | January 22, 2018 | [5 empty] | January 29, 2018 | [5 empty] | February 5, 2018 | [5 empty] | February 12, 2018 | [5 empty] | February 19, 2018 | [5 empty] | February 26, 2018 | [5 empty] | March 05, 2018 | [5 empty] | March 12, 2018 | [5 empty] | March 19, 2018 | [5 empty] | March 26, 2018 | [5 empty] | April 02, 2018 | [5 empty] | April 09, 2018
Task Name | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S
1 Documents for Prelims | bar: January 15, 2018 M to February 5, 2018 W
1.1 Finalised Chapter 1 | bar: January 15, 2018 M
1.2 Finalised Chapter 2 | bar: January 15, 2018 T
1.3 Revised Chapter 3 | bar: January 15, 2018 W to January 22, 2018 T
1.4 Revised UML Diagrams | bar: January 22, 2018 W to January 29, 2018 T
1.5 Advisers Evaluation | bar: January 29, 2018 W to February 5, 2018 W
2 Documents for Midterms | bar: February 5, 2018 T to March 05, 2018 W
2.1 Final UML Diagrams | bar: February 5, 2018 T to February 12, 2018 T
2.2 Final Chapter 3 | bar: February 12, 2018 W to March 05, 2018 W
3 Documents for Finals | bar: March 05, 2018 T to April 02, 2018 S
3.1 Complete Manuscript | bar: March 05, 2018 T to March 12, 2018 M
3.2 Endorsement from Adviser | bar: March 12, 2018 T
3.3 Revised Document | bar: March 12, 2018 W to March 26, 2018 S
3.4 Manuscript Book | bar: April 02, 2018 M to April 02, 2018 T
3.5 ACM format of Thesis | bar: April 02, 2018 F to April 02, 2018 S